## Sheet1
STT | Tên nhân sự | Mã dự án | Mô tả công việc | Tên nhân sự - filter | Mã dự án - filter | Thời gian bắt đầu | Thời gian kết thúc | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29
1 | Nguyễn Song Hào | ES192-5-A2302 | Làm việc với anh Tây để xác định lại tuyến cáp quang | Nguyễn Song Hào | ES192-5-A2302 | 2025-03-06 | 2025-03-07 | [38 empty] | 3.5 ¦ V | 3.5 ¦ V
|  |  | Làm việc với anh Tây, Thầu phụ để xác định chiều dài cáp quang | Nguyễn Song Hào | ES192-5-A2302 | 2025-03-10 | 2025-03-10 | [42 empty] | 6.0 ¦ S
| Phạm Xuân Thịnh | ES296-A2402 | Installing and verifying the electrical connection of equipments inside MCC and PLC Cabinet. | Phạm Xuân Thịnh | ES296-A2402 | 2025-05-05 | 2025-05-06 | 8.0 ¦ S | 8.0 ¦ S
|  |  | Power up and verify the connection of installed equipments | Phạm Xuân Thịnh | ES296-A2402 | 2025-05-07 | 2025-05-07 |  |  | 8.0 ¦ S
|  |  | Loading PLC program and SCADA system | Phạm Xuân Thịnh | ES296-A2402 | 2025-05-07 | 2025-05-07 |  |  | 8.0 ¦ S
|  |  | Loop test instrument devices | Phạm Xuân Thịnh | ES296-A2402 | 2025-05-08 | 2025-05-09 |  |  |  | 8.0 ¦ S | 8.0 ¦ S
|  |  | Loop test instrument devices, setting value and testing motor | Phạm Xuân Thịnh | ES296-A2402 | 2025-05-19 | 2025-05-23 | [14 empty] | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S
|  |  | Internal function test | Phạm Xuân Thịnh | ES296-A2402 | 2025-05-26 | 2025-05-30 | [21 empty] | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S
|  |  | Function test with customer | Phạm Xuân Thịnh | ES296-A2402 | 2025-06-02 | 2025-06-03 | [28 empty] | 8.0 ¦ S | 8.0 ¦ S
|  |  | Interlock sequence test | Phạm Xuân Thịnh | ES296-A2402 | 2025-06-04 | 2025-06-04 | [30 empty] | 8.0 ¦ S
|  |  | Run test the system with water | Phạm Xuân Thịnh | ES296-A2402 | 2025-06-05 | 2025-06-06 | [31 empty] | 8.0 ¦ S | 8.0 ¦ S
|  |  | Run test the system with real material | Phạm Xuân Thịnh | ES296-A2402 | 2025-06-09 | 2025-06-10 | [35 empty] | 8.0 ¦ S | 8.0 ¦ S
2 | Lê Hoàng Phúc | ES192-5-A2302 | Làm việc với anh Tây để xác định lại tuyến cáp quang | Lê Hoàng Phúc | ES192-5-A2302 | 2025-03-06 | 2025-03-07 | [38 empty] | 3.5 ¦ V | 3.5 ¦ V
|  |  | Làm việc với anh Tây, Thầu phụ để xác định chiều dài cáp quang | Lê Hoàng Phúc | ES192-5-A2302 | 2025-03-10 | 2025-03-10 | [42 empty] | 6.0 ¦ S
| Ngô Hoài Phúc | ES296-A2402 | Installing and verifying the electrical connection of equipments inside MCC and PLC Cabinet. | Ngô Hoài Phúc | ES296-A2402 | 2025-05-05 | 2025-05-06 | 8.0 ¦ S | 8.0 ¦ S
|  |  | Power up and verify the connection of installed equipments | Ngô Hoài Phúc | ES296-A2402 | 2025-05-07 | 2025-05-07 |  |  | 8.0 ¦ S
3 | Lê Vĩnh Hà | ES192-5-A2302 | Khảo sát xác định phương án lắp đặt CT | Lê Vĩnh Hà | ES192-5-A2302 | 2025-03-11 | 2025-03-12 | [43 empty] | 12.0 ¦ V | 12.0 ¦ V
|  |  | Khảo sát xác định phương án đi dây tín hiệu dòng điện, điện áp | Lê Vĩnh Hà | ES192-5-A2302 | 2025-03-13 | 2025-03-20 | [45 empty] | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S
|  |  | Khảo sát xác định phương án đi dây RS485 | Lê Vĩnh Hà | ES192-5-A2302 | 2025-03-20 | 2025-03-21 | [52 empty] | 3.0 ¦ V | 3.0 ¦ V
|  |  | Lên BOQ 1 - thiết bị Moxa để đáp ứng tiến độ | Lê Vĩnh Hà | ES192-5-A2302 | 2025-03-22 | 2025-03-24 | [54 empty] | 5.33 ¦ S | 5.33 ¦ S | 5.33 ¦ S
|  |  | Lên BOQ tủ rack, tủ trung gian, CT | Lê Vĩnh Hà | ES192-5-A2302 | 2025-03-24 | 2025-03-28 | [56 empty] | 2.0 ¦ S | 2.0 ¦ S | 2.0 ¦ S | 2.0 ¦ S | 2.0 ¦ S
|  |  | Thi công kéo cáp quang từ các trạm về phòng trung tâm | Lê Vĩnh Hà | ES192-5-A2302 | 2025-04-03 | 2025-05-15 | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | [55 empty] | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S
|  |  | Lắp đặt CT, đồng hồ, đấu nối dây tín hiệu điện áp, dòng vào đồng hồ | Lê Vĩnh Hà | ES192-5-A2302 | 2025-04-03 | 2025-07-16 | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | [28 empty] | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S
|  |  | Kéo dây cáp Ethernet từ tủ trung gian SignatureShow về phòng trung tâm | Lê Vĩnh Hà | ES192-5-A2302 | 2025-04-03 | 2025-04-16 | [66 empty] | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V
|  |  | Tích hợp tủ trung gian | Lê Vĩnh Hà | ES192-5-A2302 | 2025-04-13 | 2025-05-23 | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | [57 empty] | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V
|  |  | Lắp đặt ODF, tủ trung gian tại các trạm | Lê Vĩnh Hà | ES192-5-A2302 | 2025-04-14 | 2025-05-04 | [77 empty] | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S
|  |  | Hàn cáp quang | Lê Vĩnh Hà | ES192-5-A2302 | 2025-05-04 | 2025-05-08 | 0.8 ¦ V | 0.8 ¦ V | 0.8 ¦ V | 0.8 ¦ V | [93 empty] | 0.8 ¦ V
|  |  | Lắp đặt tủ rack, máy tính | Lê Vĩnh Hà | ES192-5-A2302 | 2025-05-05 | 2025-05-15 | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V
|  |  | Đấu nối hoàn chỉnh hệ thống | Lê Vĩnh Hà | ES192-5-A2302 | 2025-05-09 | 2025-05-25 |  |  |  |  | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V
|  |  | Tích hợp tủ rack | Lê Vĩnh Hà | ES192-5-A2302 | 2025-05-24 | 2025-07-27 | [19 empty] | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | [60 empty] | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V
|  |  | FAT | Lê Vĩnh Hà | ES192-5-A2302 | 2025-07-28 | 2025-08-29 | [144 empty] | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S
| Trần Hoàng Tú | ES296-A2402 | Installing and verifying the electrical connection of equipments inside MCC and PLC Cabinet. | Trần Hoàng Tú | ES296-A2402 | 2025-05-05 | 2025-05-06 | 8.0 ¦ S | 8.0 ¦ S
|  |  | Power up and verify the connection of installed equipments | Trần Hoàng Tú | ES296-A2402 | 2025-05-07 | 2025-05-07 |  |  | 8.0 ¦ S
|  |  | Loading PLC program and SCADA system | Trần Hoàng Tú | ES296-A2402 | 2025-05-07 | 2025-05-07 |  |  | 8.0 ¦ S
|  |  | Loop test instrument devices | Trần Hoàng Tú | ES296-A2402 | 2025-05-08 | 2025-05-09 |  |  |  | 8.0 ¦ S | 8.0 ¦ S
|  |  | Loop test instrument devices, setting value and testing motor | Trần Hoàng Tú | ES296-A2402 | 2025-05-19 | 2025-05-23 | [14 empty] | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S
|  |  | Internal function test | Trần Hoàng Tú | ES296-A2402 | 2025-05-26 | 2025-05-30 | [21 empty] | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S
|  |  | Function test with customer | Trần Hoàng Tú | ES296-A2402 | 2025-06-02 | 2025-06-03 | [28 empty] | 8.0 ¦ S | 8.0 ¦ S
|  |  | Interlock sequence test | Trần Hoàng Tú | ES296-A2402 | 2025-06-04 | 2025-06-04 | [30 empty] | 8.0 ¦ S
|  |  | Run test the system with water | Trần Hoàng Tú | ES296-A2402 | 2025-06-05 | 2025-06-06 | [31 empty] | 8.0 ¦ S | 8.0 ¦ S
|  |  | Run test the system with real material | Trần Hoàng Tú | ES296-A2402 | 2025-06-09 | 2025-06-10 | [35 empty] | 8.0 ¦ S | 8.0 ¦ S
4 | Lê Hoàng | ES192-5-A2302 | Khảo sát xác định phương án lắp đặt CT | Lê Hoàng | ES192-5-A2302 | 2025-03-11 | 2025-03-12 | [43 empty] | 12.0 ¦ V | 12.0 ¦ V
|  |  | Khảo sát xác định phương án đi dây tín hiệu dòng điện, điện áp | Lê Hoàng | ES192-5-A2302 | 2025-03-13 | 2025-03-20 | [45 empty] | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S
|  |  | Khảo sát xác định phương án đi dây RS485 | Lê Hoàng | ES192-5-A2302 | 2025-03-20 | 2025-03-21 | [52 empty] | 3.0 ¦ V | 3.0 ¦ V
|  |  | Thi công kéo cáp quang từ các trạm về phòng trung tâm | Lê Hoàng | ES192-5-A2302 | 2025-04-03 | 2025-05-15 | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | [55 empty] | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S | 0.98 ¦ S
|  |  | Lắp đặt CT, đồng hồ, đấu nối dây tín hiệu điện áp, dòng vào đồng hồ | Lê Hoàng | ES192-5-A2302 | 2025-04-03 | 2025-07-16 | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | [28 empty] | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S | 0.99 ¦ S
|  |  | Kéo dây cáp Ethernet từ tủ trung gian SignatureShow về phòng trung tâm | Lê Hoàng | ES192-5-A2302 | 2025-04-03 | 2025-04-16 | [66 empty] | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V | 0.93 ¦ V
|  |  | Tích hợp tủ trung gian | Lê Hoàng | ES192-5-A2302 | 2025-04-13 | 2025-05-23 | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | [57 empty] | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V
|  |  | Lắp đặt ODF, tủ trung gian tại các trạm | Lê Hoàng | ES192-5-A2302 | 2025-04-14 | 2025-05-04 | [77 empty] | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S | 0.95 ¦ S
|  |  | Hàn cáp quang | Lê Hoàng | ES192-5-A2302 | 2025-05-04 | 2025-05-08 | 0.8 ¦ V | 0.8 ¦ V | 0.8 ¦ V | 0.8 ¦ V | [93 empty] | 0.8 ¦ V
|  |  | Lắp đặt tủ rack, máy tính | Lê Hoàng | ES192-5-A2302 | 2025-05-05 | 2025-05-15 | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V | 0.91 ¦ V
|  |  | Đấu nối hoàn chỉnh hệ thống | Lê Hoàng | ES192-5-A2302 | 2025-05-09 | 2025-05-25 |  |  |  |  | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V | 0.94 ¦ V
|  |  | Tích hợp tủ rack | Lê Hoàng | ES192-5-A2302 | 2025-05-24 | 2025-07-27 | [19 empty] | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | [60 empty] | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V | 0.98 ¦ V
|  |  | FAT | Lê Hoàng | ES192-5-A2302 | 2025-07-28 | 2025-08-29 | [144 empty] | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S | 0.97 ¦ S
| Võ Kinh Đô | ES296-A2402 | Installing and verifying the electrical connection of equipments inside MCC and PLC Cabinet. | Võ Kinh Đô | ES296-A2402 | 2025-05-05 | 2025-05-06 | 8.0 ¦ S | 8.0 ¦ S
|  |  | Power up and verify the connection of installed equipments | Võ Kinh Đô | ES296-A2402 | 2025-05-07 | 2025-05-07 |  |  | 8.0 ¦ S
5 | Nguyễn Lâm Hữu Thiên |  | Loading PLC program and SCADA system | Nguyễn Lâm Hữu Thiên | ES296-A2402 | 2025-05-07 | 2025-05-07 |  |  | 8.0 ¦ S
|  |  | Loop test instrument devices | Nguyễn Lâm Hữu Thiên | ES296-A2402 | 2025-05-08 | 2025-05-09 |  |  |  | 8.0 ¦ S | 8.0 ¦ S
|  |  | Loop test instrument devices, setting value and testing motor | Nguyễn Lâm Hữu Thiên | ES296-A2402 | 2025-05-19 | 2025-05-23 | [14 empty] | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S
|  |  | Internal function test | Nguyễn Lâm Hữu Thiên | ES296-A2402 | 2025-05-26 | 2025-05-30 | [21 empty] | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S | 8.0 ¦ S
|  |  | Function test with customer | Nguyễn Lâm Hữu Thiên | ES296-A2402 | 2025-06-02 | 2025-06-03 | [28 empty] | 8.0 ¦ S | 8.0 ¦ S
|  |  | Interlock sequence test | Nguyễn Lâm Hữu Thiên | ES296-A2402 | 2025-06-04 | 2025-06-04 | [30 empty] | 8.0 ¦ S
|  |  | Run test the system with water | Nguyễn Lâm Hữu Thiên | ES296-A2402 | 2025-06-05 | 2025-06-06 | [31 empty] | 8.0 ¦ S | 8.0 ¦ S
|  |  | Run test the system with real material | Nguyễn Lâm Hữu Thiên | ES296-A2402 | 2025-06-09 | 2025-06-10 | [35 empty] | 8.0 ¦ S | 8.0 ¦ S
| Nguyễn Văn Hoàng Đông | ES192-5-A2302 | Khảo sát xác định phương án lắp đặt CT | Nguyễn Văn Hoàng Đông | ES192-5-A2302 | 2025-03-11 | 2025-03-12 | [43 empty] | 12.0 ¦ V | 12.0 ¦ V
|  |  | Khảo sát xác định phương án đi dây tín hiệu dòng điện, điện áp | Nguyễn Văn Hoàng Đông | ES192-5-A2302 | 2025-03-13 | 2025-03-20 | [45 empty] | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S | 1.5 ¦ S
|  |  | Khảo sát xác định phương án đi dây RS485 | Nguyễn Văn Hoàng Đông | ES192-5-A2302 | 2025-03-20 | 2025-03-21 | [52 empty] | 3.0 ¦ V | 3.0 ¦ V
|  |  | Lên BOQ 2 - thiết bị phần cứng, phần mềm đã có mã sales bóc sẵn | Nguyễn Văn Hoàng Đông | ES192-5-A2302 | 2025-03-21 | 2025-03-21 | [53 empty] | 8.0 ¦ V
6 | Nguyễn Song Hào | ES296-A2402 | SAT & Handover | Nguyễn Song Hào | ES296-A2402 | 2025-06-11 | 2025-06-11 | [37 empty] | 8.0 ¦ V
7 | Ngô Thị Vân |  | SAT & Handover | Ngô Thị Vân | ES296-A2402 | 2025-06-11 | 2025-06-11 | [37 empty] | 8.0 ¦ V